IMP-31: October Decision

Hashelee Anuththara    |    Supervisor: Gunanathan Poorvi

My decision: in October I'll focus on the tabular side first (cross-validation, baseline models and the missing-information tests on the Kottarathil data), while starting on USOVA3D access and inspection at the same time, so that any problems with the ultrasound data come up early.

I want to be upfront that this is a planning decision, not one based on model results, because I haven't run any models yet. I'm happy to change it after talking it through with my supervisor.

# The options I weighed up

| Option | In favour | Against |
| --- | --- | --- |
| A. Tabular first, USOVA3D access alongside (my choice) | The data and pipeline are ready; it tests the main gap (missing information); I can get first results quickly | The ultrasound work starts later |
| B. Follicle segmentation first | Deals with the riskiest part early | Needs deep-learning tools I haven't learned yet; only 16 labelled volumes; if it stalls I'd have nothing to show for weeks |
| C. Both equally | Keeps both parts moving | Splits my time while I'm still learning, so both would move slowly |

# Why I'm starting with the tabular work

The simplest reason is that it's ready. The dataset is audited, grouped and cleaned (IMP-02 to IMP-06), so I can move straight on to the next tasks without waiting for anything.

It's also where the main contribution of the project sits. The main research gap (G3, models breaking when information is missing) and sub-gap 2 are both tested on the tabular data.

The literature review gave me another reason. When I went through the published PCOS models for RP-04, most of them reported 93–100% accuracy, but many had let test data leak into training, for example by running SMOTE before splitting the data. Only one tested on a different dataset, and there the F1 for PCOS dropped to about 60–63%. That convinced me that a clean, stratified cross-validation set-up (IMP-07) has to come first, because every later result depends on it.

Finally, RP-05 and RP-06 already settled which models to compare: Logistic Regression as the simple baseline, then Random Forest, XGBoost and CatBoost, with TabPFN as a strong option for small data. Since those choices are made, I can start building straight away.

# Why USOVA3D can't wait until November

I don't want to leave the ultrasound data untouched for a whole month. The database needs a login at usova3d.um.si, and I don't know how long that will take. Only 16 of its 35 volumes come with labels I can train on (the other 19 are scored through the portal), so I need to see the files before I can plan the model properly. The segmentation work also needs tools I've never used, like deep learning and 3D image files, so the sooner I start learning them the better. There's also a counting problem to solve: the guideline only counts follicles of 2–9 mm, but USOVA3D outlines every follicle.

# My plan for October

| Week | Tabular work | Ultrasound work |
| --- | --- | --- |
| 12–18 Oct | IMP-07 stratified and nested cross-validation with seed 42 IMP-08 to IMP-12 baselines (LR, RF, XGBoost, CatBoost, SVM) | IMP-13 request access and download USOVA3D |
| 19–25 Oct | IMP-15 to IMP-19 scenarios B1–B4 and comparing them IMP-20, IMP-21 missing-information scenarios M0–M5 | IMP-14 open the volumes and masks; first visualisation notebook |
| 26 Oct – 1 Nov | IMP-26, IMP-27 run the models with information missing; compare simple ways of handling it | Start learning the segmentation tools and plan IMP-22 |
| November | Write up the tabular results | IMP-22 to IMP-25, IMP-28, IMP-29 segmentation and follicle counting |

# What could go wrong

| Risk | What I'll do about it |
| --- | --- |
| USOVA3D access is slow or refused | Email the database administrator (usova3d@um.si) and keep going with the tabular work. If I still don't have access by 25 October, I'll agree a smaller follicle-counting scope with my supervisor. |
| The cleaning decisions or groupings aren't approved | They stay as 'proposed' in the Excel file. The pipeline reads that file, so it updates automatically when a decision changes. |
| Learning the new tools takes longer than I expect | Practise each one in a small notebook before using it in the project, and keep IMP-22 onwards in November as planned above. |
| The results look too good | Check for leakage first: SMOTE, feature selection or imputation fitted outside the training folds. |

# How I'll judge whether October went well

By the end of October I want to have one stratified cross-validation set-up with a fixed seed that every model uses, and a results table for the baseline models showing recall, specificity, F1, ROC-AUC and PR-AUC. I also want the four information scenarios (B1–B4) compared, the missing-information scenarios (M0–M5) defined with first results showing how much performance drops, and USOVA3D downloaded with some volumes and masks visualised.